## Risk Register
Risk Register – NorthStar Digital Personal Health Companion App (MVP)
IT505 Group Project – Task 4 ¦ Date: March 28, 2026
ID No. | Rank | Risk Name | Description | Category | Root Cause | Triggers | Potential Responses | Risk Owner | Probability | Impact | Status
R-01 | 1 | Data Security Breach | The application stores and retrieves the users' sensitive health information including but limited to their medical condition(s), allergy(is) and/or intolerance(s), blood group, emergency contact(s), etc. As such it represents a significant risk with respect to potential malicious hacking attempts to obtain unauthorized access to the users' sensitive health information, intercepting users' data during transmission or breaching the stored users' sensitive health information on mobile devices and backend server systems without proper security protocols and measures being implemented. | External / Technical | Storage and collection of users' sensitive health information on mobile devices and backend servers without implementing appropriate security protocols. | Third party security audits identifying and reporting on suspicious activity from login access to attempted unauthorized access to users' sensitive health information. | Implementation: Encrypt all users' sensitive health information using end-to-end encryption when collected and stored by the application. Perform frequent penetration testing. Establish role-based access controls. Prior to launching the MVP develop, implement, and test a comprehensive Incident Response Plan. | Mobile Developer / QA Lead | Medium (3/5) | Very High (5/5) | CRITICAL – Score: 15
R-02 | 2 | Regulatory Non-Compliance (PIPEDA / HIPAA) | The App collects personally identifiable Health Information (PHI), and therefore there are potential risks associated with failing to meet Canadian Privacy Law Requirements (PIPEDA) and/or relevant U.S. Regulations (HIPAA) that may apply depending on how the application will be promoted across international borders. Potential sanctions for non-compliance include fines, legal actions against both individuals involved in the collection and use of PHI, and forced cessation of the App. | External / Legal | There was no legal review of the Data Handling Practices included in the Design Phase; and limited knowledge of the Health Data Privacy Obligations among members of the Development Team. | Regulatory Body Inquiry; Legal Counsel notifies of Un-Reviewed Data Handling Practices; App Store Compliance Review Fails | Reduce Risk: Hire a lawyer/Privacy Consultant at the beginning of the Requirements Phase; complete a Privacy Impact Assessment (PIA) prior to launching the App. Include Consent Management and Data Deletion Options as part of the Minimum Viable Product (MVP) Scope. | Project Manager | Medium-High (4/5) | High (4/5) | HIGH – Score: 16
R-03 | 3 | Personnel Skill Gap / Understaffing | The project budget has allocated $90,000 to develop applications using mobile platforms and $25,000 per role to support both UI/UX Design and Quality Assurance. It is difficult to attract skilled programmers who are capable of developing software that runs on both Android and iOS when working inside a constrained budget. In addition, several roles from the project charter have yet to be filled by a qualified candidate. | Internal / Resource | Budgetary limitations hinder the ability to acquire talented individuals. A cross-functionally structured small team limits the amount of redundancy. | A key role in the project was vacant at sprint start; failed to meet velocity goals set for each sprint; programmer reported they were unfamiliar with either React Native or Swift/Kotlin. | Mitigate/Accept: Hire personnel during the initial two weeks of the project. Cross-train other team members on secondary skills. Utilize Agile sprint review sessions to identify underperformance as soon as possible. Identify contingency contractors to utilize up to the full extent of the $15,000 reserve budget. | Project Manager | High (4/5) | High (4/5) | HIGH – Score: 16
R-04 | 4 | Compressed Timeline / Schedule Overrun | A 4-month timeline from April 1 through July 31, 2026 is overly ambitious for a mobile app intended to be on multiple platforms since it includes passing an accessibility standard, QA, and all of the review phases required by each App Store for both Android and iOS. | Internal / Schedule | The Business-Driven Timeline targets early market access; Underestimated the amount of time required to develop/comply with dual-platform development requirements. | Month 1 Sprint Velocity less than Target. Submission to one of the App Stores was denied; QA revealed several high-risk issues that require major re-work. | Mitigate: Employ Timeboxed Agile Sprints where every sprint has clearly identified goals. When time becomes an issue, de-prioritize non-core functionality as early as possible. Submit to the App Stores at least two weeks prior to the Final Deadline to account for review cycles. Proactively use Contingency Reserve. | Project Manager | High (4/5) | Medium (3/5) | HIGH – Score: 12
R-05 | 5 | Low-Quality MVP / Excessive Defects | Under schedule pressure, the development team may release an MVP with critical bugs and missing features that will negatively affect early user perception and skin the feedback collected which makes it difficult to make good decisions for Version 2. | Internal / Quality | The compressed timeline reduces the amount of time that will be allocated to quality assurance activities; the development team did not have sufficient time to test the application on multiple Android and iOS device variants; feature creep pushed back testing phases. | The QA log indicates that the critical defect rate was greater than the established threshold; UAT identified major usability issues; users reported application crashes during demo. | Mitigate: establish a minimum defect threshold for release of an MVP within the Definition of Done. Establish dedicated QA sprints. Implement automated testing tools (i.e. Appium) for regression testing across platforms. Ensure the QA lead has early involvement in sprint reviews, not just at the end. | QA Lead | Medium (3/5) | Medium (3/5) | MODERATE – Score: 9
R-06 | 6 | Limited Market Validation from Target Users | The primary target audience consists of seniors with little to no smartphone proficiency. Thus, those providing MVP feedback as early adopters will most likely be younger and technically proficient users, and therefore their feedback may not accurately represent the wants or actions of the intended audience. | External / Market | A digital divide exists between the early adopter groups and the desired senior population; a lack of formalized user research was conducted using older adult test subjects at the time of product design. | The age distribution of the beta testers was younger than the target demographic; every participant in the usability testing had previous experience with apps; accessibility issues surfaced upon launching. | Mitigate: Partner with community-based organizations or local retirement communities to enable inclusion of older adult users in usability testing. Identify specific accessibility requirements (e.g. WCAG 2.1 AA) to establish acceptable levels of accessibility. Have the Marketing Representative assist in contacting a representative sample of beta testers from the target demographics. | Marketing Rep / UI/UX Designer | Medium-High (4/5) | Medium (3/5) | HIGH – Score: 12

## References
APA References – IT505 Task 4 Risk Register
Kendrick, T. (2015). Identifying and managing project risk: Essential tools for failure-proofing your project (3rd ed.). AMACOM.
Office of the Privacy Commissioner of Canada. (2019). A guide for individuals: Protecting your privacy. Government of Canada. https://www.priv.gc.ca
Project Management Institute. (2021). A guide to the project management body of knowledge (PMBOK guide) (7th ed.). Project Management Institute.
Project Management Institute. (2019). Practice standard for project risk management. Project Management Institute.
U.S. Department of Health & Human Services. (2023). Summary of the HIPAA security rule. HHS.gov. https://www.hhs.gov/hipaa/for-professionals/security/laws-regulations/index.html