## Slide 1
NorthStar Digital
Personal Health Companion App (MVP)
IT505 Group Project — Project Management Plan
Pooja Sharma · Oji Nkechi · Oluwakayode Soyinka · Dominick Tressler
Concordia University of Edmonton · March 31, 2026

## Slide 2: Presentation overview
Background, objectives, and constraints
MVP scope, WBS, and change control
Schedule (Apr 1 – Jul 31, 2026) and Agile delivery
Risk analysis — six prioritized risks with responses
Stakeholder register, power/interest matrix, and communications
Key conclusions

## Slide 3: Background & strategic context
NorthStar Digital Solutions — growing startup; mobile productivity and wellness apps.
Next growth area: digital health — users increasingly manage health on smartphones.
MVP goal: launch quickly, test demand, learn from early adopters (especially older adults).
Product: simple, intuitive app for health tracking, medications, and emergency contacts.

## Slide 4: Objectives & project constraints
Deliver a mobile health companion within four months (Apr 1 – Jul 31, 2026).
Give users simple recording of health data and emergency contacts.
Ship an MVP to the market and gather structured feedback.
Demonstrate NorthStar’s ability to deliver a reliable health-related mobile solution.
Constraints: $200,000 budget · 4 months · small cross-functional team · Agile.

## Slide 5: MVP — Core features (initial release)
Health tracker — blood pressure, daily exercise, weight, well-being notes.
Medication reminder — schedule, push notifications, medication notes.
Medical contacts directory — doctors, clinics, pharmacies, emergency contacts.
Emergency information card — allergies, conditions, blood type, emergency contacts; quick access in emergencies.

## Slide 6: Design requirements
Simple to use; accessible to older adults; secure and privacy-conscious.
Android and iOS compatibility.
Clear navigation, large readable fonts, minimal setup steps.
Scope emphasizes usability and trust — not feature overload.

## Slide 7: Budget allocation ($200,000 total)
Project management — $25,000
Mobile development — $90,000
UI/UX design — $25,000
Quality assurance — $25,000
Marketing & launch — $20,000
Contingency reserve — $15,000

## Slide 8: Project success criteria
Complete within 4 months and within $200,000.
Core features work on both Android and iOS.
Meet usability and accessibility expectations.
No critical security or privacy gaps at release.
MVP launched and user feedback collected.

## Slide 9: Project approach (Agile)
Iterative development with continuous feedback across the lifecycle.
Phases: initiation & planning → requirements & scope → UI/UX design/prototyping → incremental core development → QA → MVP launch & feedback.
Small cross-functional team; regular reviews and sprint cycles.
Project Manager: Oji Nkechi — charter dated March 26, 2026.

## Slide 10: Scope statement (summary)
In scope
Reliable, simple health app for Android/iOS in four months.
Health tracker (BP, exercise, weight, notes).
Medication reminder (schedule, notifications, notes).
Medical contacts & emergency card (allergies, blood type, conditions).
Large fonts, clear navigation, secure privacy-conscious architecture.
Out of scope
Advanced diagnostic tools.
Wearable hardware integration (e.g. smartwatches).
Desktop and web versions.

## Slide 11: Work breakdown structure (WBS)
1 — Project management: initiation (charter, stakeholders); sprint planning & backlog.
2 — UI/UX: interface design (accessibility, large type); prototypes & navigation flow.
3 — App development: health tracker; medication reminder & notifications; contacts & emergency card DB.
4 — QA: cross-platform testing; accessibility & usability testing.
5 — Deployment & launch: App Store/Google Play submission; early-adopter feedback.

## Slide 12: Deliverable verification & scope change
Verification: phase/sprint reviews; compare to acceptance criteria; functional, usability, compatibility testing; stakeholder sign-off; document acceptance or revisions.
Changes: document new requests in the product backlog; PM assesses impact on $200k budget and 4-month timeline.
Approved changes may defer lower-priority MVP items to a later version to protect the release date.

## Slide 13: High-level schedule (4 months)
Month 1 (April 2026): Project initiation; requirements; backlog; UI/UX foundations & early prototypes.
Month 2 (May): Complete UI/UX; sprint development — health tracker & medication modules.
Month 3 (June): Contacts & emergency card; integration; begin structured QA cycles.
Month 4 (July): Full QA & accessibility; App Store submissions ≥2 weeks before deadline; MVP launch & feedback collection.
Note: Submit to stores early to allow Apple/Google review cycles; use contingency reserve if needed.

## Slide 14: Risk management approach
PMI/PMBOK: individual project risks (resources, time) vs. overall project risk (environment).
Qualitative analysis (probability × impact, 1–5 scales) — appropriate for MVP planning stage.
Score bands: 15–25 Critical · 10–14 High · 5–9 Moderate · 1–4 Low.
Keep the risk register current via sprint retrospectives and phase-gate reviews.

## Slide 15: Risk register — priority summary
R-01 Data security breach — Technical — P×I → 15 — CRITICAL — Mitigate
R-02 Regulatory non-compliance (PIPEDA/HIPAA) — Legal — 16 — HIGH — Mitigate
R-03 Personnel skill gap / understaffing — Resource — 16 — HIGH — Mitigate/Accept
R-04 Compressed timeline / schedule overrun — Schedule — 12 — HIGH — Mitigate
R-05 Low-quality MVP / excessive defects — Quality — 9 — MODERATE — Mitigate
R-06 Limited market validation (seniors vs. beta testers) — Market — 12 — HIGH — Mitigate

## Slide 16: Top risks — security & compliance
R-01 Data security breach: PHI on device/server — risk of unauthorized access or interception.
Response: E2E encryption; penetration testing; RBAC; incident response plan before MVP launch. Owner: Mobile Dev / QA Lead.
R-02 Regulatory: PHI collection — PIPEDA/HIPAA exposure; fines, legal action, or app cessation.
Response: legal/privacy consultant early; privacy impact assessment (PIA); consent & data deletion in MVP. Owner: Project Manager.

## Slide 17: Risks — people, schedule, quality, market
R-03: Hire early; cross-train; agile reviews; contingency contractors (up to $15k reserve). PM owns.
R-04: Timeboxed sprints; de-prioritize non-core work; submit stores 2+ weeks early. PM owns.
R-05: Definition of Done with defect thresholds; QA sprints; Appium-style automation; QA in sprint reviews. QA Lead owns.
R-06: Partner with seniors’ organizations; WCAG 2.1 AA; marketing recruits representative beta testers. Marketing/UI-UX.

## Slide 18: Risk analysis — conclusions
Security and compliance carry the highest long-term consequence (legal, financial, reputation).
Internal delivery risks (personnel, schedule) are acute in a small Agile team with limited redundancy.
Market validation affects roadmap after MVP more than day-one delivery — still plan for representative older-adult testing.

## Slide 19: Stakeholder register (10 stakeholders)
NorthStar leadership — sponsor; on-time/budget launch; bi-weekly executive reports.
PM (Oji Nkechi) — delivery; sprint coordination; central communication hub.
Mobile developer — stable requirements; sprint planning from day one; clear acceptance criteria.
UI/UX designer — older-adult usability; early usability check-ins; personas & wireframes.
QA lead — time to test; sprint reviews; cross-platform test plans.
Marketing rep — audience fit; launch & MVP feedback plan.
End users (incl. older adults) — simplicity, privacy; beta & in-app feedback.
Healthcare professionals — clarity it is a personal tool, not a medical device; optional design review.
App stores (Apple/Google) — compliance with privacy/security rules; early guideline review.
Regulators (privacy) — PIPEDA-aligned handling; PIA; minimize data; document decisions.

## Slide 20: Power / interest matrix
Manage closely — Project Manager, end users (high interest; users indirect but essential).
Keep satisfied — App stores, regulatory bodies, NorthStar leadership (high influence; compliance & funding).
Keep informed — Mobile developer, UI/UX, QA, marketing (core team).
Monitor — Healthcare professionals (lower influence; endorsement still valuable).

## Slide 21: Stakeholder communication plan
Leadership: executive status report + email — bi-weekly — Project Manager.
Project team: sprint planning, stand-ups, retrospectives — daily / per sprint — PM.
End users: beta program, in-app feedback — post-MVP launch — Marketing representative.
App stores: guideline compliance embedded in schedule; submission milestones tracked early.
Principle: right information, right audience, right time — avoid unnecessary noise.

## Slide 22: Key takeaways
Clear MVP scope, WBS, and Agile cadence align delivery with a fixed 4-month budget window.
Privacy, security, and regulation are prioritized alongside schedule and quality risks.
Stakeholder and communication plans keep sponsors, stores, regulators, and users appropriately engaged.
Next steps: execute sprints, maintain the risk register, and submit to app stores with buffer before Jul 31, 2026.

## Slide 23
Thank you
Questions?